## Compare
Four scenarios · Sep–Dec 2026 · one clock (sales targets)
3.0 = base mining plan · 3.1 = +330 kt/month BLB LIM Oct–Dec (the sales table already contains it). .1 = all leftover LD trucks to HUAFEI/BSE · .2 = half to POS 6 from October. All targets are the sales lines distributed over months in the plan shape.
Scenario | Year sales target | Predicted plan | Coverage | SAP % | LIM-TOS % | LIM-LD % | Dec DT
3.0.1 | 17003193 | 16453539 | 96.8% | 100.5% | 100.5% | 92.15% | 1190
3.0.2 | 17003193 | 16941732 | 99.6% | 100.5% | 100.6% | 98.5% | 1190
3.1.1 | 17003193 | 16580201 | 97.5% | 100.5% | 100.3% | 92.95% | 1052
3.1.2 | 17003193 | 16974809 | 99.8% | 100.5% | 100.3% | 98.89% | 1052
Month by month — Predicted % of the distributed sales target
Month | 3.0.1 | 3.0.2 | 3.1.1 | 3.1.2
Sep | 96.2% | 96.2% | 96.2% | 96.2%
Oct | 93.2% | 97.1% | 93.5% | 96.8%
Nov | 95% | 98.8% | 96% | 99.4%
Dec | 101.7% | 104.1% | 103.3% | 104.9%
Reading: every month judges its share of the sales target. December is the only month above 100% in all four scenarios — the December sheet gives the two options to land it at exactly 100%.
Month by month — Predicted tonnes
Month | 3.0.1 | 3.0.2 | 3.1.1 | 3.1.2
Sep | 2381536 | 2381536 | 2381536 | 2381536
Oct | 3722205 | 3880040 | 3912780 | 4048623
Nov | 5133077 | 5336369 | 5314484 | 5499416
Dec | 5216721 | 5343787 | 4971401 | 5045234
TOTAL | 16453539 | 16941732 | 16580201 | 16974809

## December options
December runs over target in every scenario — two ways to spend the surplus
Option 1: park the surplus DT (total month lands at 100.0%). Option 2: cut LIM-LD to exactly its December line and re-dispatch every freed DT to KR>FENI KM0 + TF>FENI KM0 — the hauled material is kilnable SAP feed stocked at the plant.
Scenario 3.0.1 — December
| Target t | Predicted t | Coverage | Fleet DT
As frozen | 5131386 | 5216721 | 101.7% | 1190
OPTION 1 · park 26 DT (total month → 100.0%) | 5131386 | 5132370 | 100% | 1164
OPTION 2 · re-dispatch 56 DT (LIM-LD → 100.0%) | 5131386 | 5248586 | 102.3% | 1190 | + 213,461 t SAP stocked at FeNi KM0
Option 2 cut (sized so LIM-LD lands exactly on its line): TF>HUAFEI (RIM, LD): −56 DT @ 104.7 t/day/DT
OPTION 2 — full December plan (re-dispatched)
Route | Contractor | Material | DT before | DT after | Δ DT | t/day | t/month
TF>HUAFEI | RIM | LIM-LD | 437 | 381 | -56 | 39874 | 1236106
TF>HUAFEI | SMA | LIM-LD | 150 | 150 | 0 | 15675 | 485925
BLB>HUAFEI | RIM | LIM-TOS | 95 | 95 | 0 | 23250 | 720750
TF>HUAFEI | RIM | LIM-TOS | 62 | 62 | 0 | 6489 | 201159
KR>HUAFEI | SMA | LIM-TOS | 19 | 19 | 0 | 2563 | 79453
BLB>FENI KM0 | RIM | SAP | 202 | 202 | 0 | 45786 | 1419366
TF>FENI KM15 | RIM | SAP | 140 | 140 | 0 | 14736 | 456816
KR>FENI KM15 | SMA | SAP | 50 | 50 | 0 | 7958 | 246698
BLB>POS 14 | RIM | SAP | 7 | 7 | 0 | 2044 | 63364
TF>POS 12 | RIM | SAP | 18 | 18 | 0 | 2039 | 63209
KR>POS 12 | SMA | SAP | 10 | 10 | 0 | 2009 | 62279
KR>FENI KM0 | reallocated | SAP (stock at FeNi KM0) | — | 28 | 28 | 3802 | 117848
TF>FENI KM0 | reallocated | SAP (stock at FeNi KM0) | — | 28 | 28 | 3084 | 95614
TOTAL |  |  | 1190 | 1190 |  |  | 5248587
OPTION 2 — tonnage by material (December)
Material | BEFORE re-dispatch t/mo | AFTER re-dispatch t/mo | Δ t/mo | Change % | December TARGET t | Coverage after
SAP | 2311732 | 2525193 | 213461 | 9.234% | 2311213 | 109.3%
LIM-TOS | 1001362 | 1001362 | 0 | 0% | 996084 | 100.5%
LIM-LD | 1903716 | 1722031 | -181685 | -9.544% | 1719964 | 100.1%
of which SAP stocked at FeNi KM0 (KR 28 DT + TF 28 DT reallocated) |  | 213461 | 213461 | inside the SAP row
TOTAL moved | 5216810 | 5248586 | 31776 | 0.6091%
Scenario 3.0.2 — December
| Target t | Predicted t | Coverage | Fleet DT
As frozen | 5131386 | 5343787 | 104.1% | 1190
OPTION 1 · park 54 DT (total month → 100.0%) | 5131386 | 5131167 | 100% | 1136
OPTION 2 · re-dispatch 79 DT (LIM-LD → 100.0%) | 5131386 | 5333821 | 103.9% | 1190 | + 301,080 t SAP stocked at FeNi KM0
Option 2 cut (sized so LIM-LD lands exactly on its line): TF>POS 6 (RIM, LD): −79 DT @ 127.0 t/day/DT
OPTION 2 — full December plan (re-dispatched)
Route | Contractor | Material | DT before | DT after | Δ DT | t/day | t/month
TF>HUAFEI | RIM | LIM-LD | 288 | 288 | 0 | 30085 | 932635
TF>POS 6 | RIM | LIM-LD | 149 | 70 | -79 | 8890 | 275605
TF>POS 6 | SMA | LIM-LD | 75 | 75 | 0 | 8701 | 269731
TF>HUAFEI | SMA | LIM-LD | 75 | 75 | 0 | 7822 | 242482
BLB>HUAFEI | RIM | LIM-TOS | 95 | 95 | 0 | 23250 | 720750
TF>HUAFEI | RIM | LIM-TOS | 62 | 62 | 0 | 6477 | 200787
KR>HUAFEI | SMA | LIM-TOS | 19 | 19 | 0 | 2549 | 79019
BLB>FENI KM0 | RIM | SAP | 202 | 202 | 0 | 45786 | 1419366
TF>FENI KM15 | RIM | SAP | 140 | 140 | 0 | 14736 | 456816
KR>FENI KM15 | SMA | SAP | 50 | 50 | 0 | 7958 | 246698
BLB>POS 14 | RIM | SAP | 7 | 7 | 0 | 2044 | 63364
TF>POS 12 | RIM | SAP | 18 | 18 | 0 | 2039 | 63209
KR>POS 12 | SMA | SAP | 10 | 10 | 0 | 2009 | 62279
KR>FENI KM0 | reallocated | SAP (stock at FeNi KM0) | — | 40 | 40 | 5424 | 168135
TF>FENI KM0 | reallocated | SAP (stock at FeNi KM0) | — | 39 | 39 | 4289 | 132945
TOTAL |  |  | 1190 | 1190 |  |  | 5333821
OPTION 2 — tonnage by material (December)
Material | BEFORE re-dispatch t/mo | AFTER re-dispatch t/mo | Δ t/mo | Change % | December TARGET t | Coverage after
SAP | 2311732 | 2612812 | 301080 | 13.02% | 2311213 | 113%
LIM-TOS | 1000556 | 1000556 | 0 | 0% | 996084 | 100.4%
LIM-LD | 2031492 | 1720453 | -311039 | -15.31% | 1719964 | 100%
of which SAP stocked at FeNi KM0 (KR 40 DT + TF 39 DT reallocated) |  | 301080 | 301080 | inside the SAP row
TOTAL moved | 5343780 | 5333821 | -9959 | -0.1864%
Scenario 3.1.1 — December
| Target t | Predicted t | Coverage | Fleet DT
As frozen | 4810381 | 4971401 | 103.3% | 1052
OPTION 1 · park 49 DT (total month → 100.0%) | 4810381 | 4811620 | 100% | 1003
OPTION 2 · re-dispatch 101 DT (LIM-LD → 100.0%) | 4810381 | 5027004 | 104.5% | 1052 | + 384,923 t SAP stocked at FeNi KM0
Option 2 cut (sized so LIM-LD lands exactly on its line): TF>HUAFEI (RIM, LD): −101 DT @ 105.2 t/day/DT
OPTION 2 — full December plan (re-dispatched)
Route | Contractor | Material | DT before | DT after | Δ DT | t/day | t/month
TF>HUAFEI | RIM | LIM-LD | 319 | 218 | -101 | 22932 | 710878
TF>HUAFEI | SMA | LIM-LD | 87 | 87 | 0 | 9142 | 283402
BLB>HUAFEI | RIM | LIM-TOS | 139 | 139 | 0 | 33859 | 1049629
TF>HUAFEI | RIM | LIM-TOS | 62 | 62 | 0 | 6522 | 202182
KR>HUAFEI | SMA | LIM-TOS | 19 | 19 | 0 | 2597 | 80507
BLB>FENI KM0 | RIM | SAP | 202 | 202 | 0 | 45786 | 1419366
TF>FENI KM15 | RIM | SAP | 140 | 140 | 0 | 14847 | 460257
KR>FENI KM15 | SMA | SAP | 49 | 49 | 0 | 7929 | 245799
TF>POS 12 | RIM | SAP | 18 | 18 | 0 | 2045 | 63395
BLB>POS 14 | RIM | SAP | 7 | 7 | 0 | 2044 | 63364
KR>POS 12 | SMA | SAP | 10 | 10 | 0 | 2042 | 63302
KR>FENI KM0 | reallocated | SAP (stock at FeNi KM0) | — | 51 | 51 | 6917 | 214423
TF>FENI KM0 | reallocated | SAP (stock at FeNi KM0) | — | 50 | 50 | 5500 | 170500
TOTAL |  |  | 1052 | 1052 |  |  | 5027004
OPTION 2 — tonnage by material (December)
Material | BEFORE re-dispatch t/mo | AFTER re-dispatch t/mo | Δ t/mo | Change % | December TARGET t | Coverage after
SAP | 2315483 | 2700406 | 384923 | 16.62% | 2311213 | 116.8%
LIM-TOS | 1332318 | 1332318 | 0 | 0% | 1326082 | 100.5%
LIM-LD | 1323632 | 994280 | -329352 | -24.88% | 992213 | 100.2%
of which SAP stocked at FeNi KM0 (KR 51 DT + TF 50 DT reallocated) |  | 384923 | 384923 | inside the SAP row
TOTAL moved | 4971433 | 5027004 | 55571 | 1.118%
Scenario 3.1.2 — December
| Target t | Predicted t | Coverage | Fleet DT
As frozen | 4810381 | 5045234 | 104.9% | 1052
OPTION 1 · park 59 DT (total month → 100.0%) | 4810381 | 4811739 | 100% | 993
OPTION 2 · re-dispatch 104 DT (LIM-LD → 100.0%) | 4810381 | 5035551 | 104.7% | 1052 | + 395,746 t SAP stocked at FeNi KM0
Option 2 cut (sized so LIM-LD lands exactly on its line): TF>POS 6 (RIM, LD): −86 DT @ 127.7 t/day/DT · TF>POS 6 (SMA, LD): −18 DT @ 116.6 t/day/DT
OPTION 2 — full December plan (re-dispatched)
Route | Contractor | Material | DT before | DT after | Δ DT | t/day | t/month
TF>HUAFEI | RIM | LIM-LD | 233 | 233 | 0 | 24482 | 758942
TF>POS 6 | RIM | LIM-LD | 86 | 0 | -86 | 0 | 0
TF>POS 6 | SMA | LIM-LD | 43 | 25 | -18 | 2915 | 90369
TF>HUAFEI | SMA | LIM-LD | 44 | 44 | 0 | 4618 | 143158
BLB>HUAFEI | RIM | LIM-TOS | 139 | 139 | 0 | 33859 | 1049629
TF>HUAFEI | RIM | LIM-TOS | 62 | 62 | 0 | 6514 | 201934
KR>HUAFEI | SMA | LIM-TOS | 19 | 19 | 0 | 2590 | 80290
BLB>FENI KM0 | RIM | SAP | 202 | 202 | 0 | 45786 | 1419366
TF>FENI KM15 | RIM | SAP | 140 | 140 | 0 | 14847 | 460257
KR>FENI KM15 | SMA | SAP | 49 | 49 | 0 | 7929 | 245799
TF>POS 12 | RIM | SAP | 18 | 18 | 0 | 2045 | 63395
BLB>POS 14 | RIM | SAP | 7 | 7 | 0 | 2044 | 63364
KR>POS 12 | SMA | SAP | 10 | 10 | 0 | 2042 | 63302
KR>FENI KM0 | reallocated | SAP (stock at FeNi KM0) | — | 52 | 52 | 7049 | 218533
TF>FENI KM0 | reallocated | SAP (stock at FeNi KM0) | — | 52 | 52 | 5717 | 177213
TOTAL |  |  | 1052 | 1052 |  |  | 5035551
OPTION 2 — tonnage by material (December)
Material | BEFORE re-dispatch t/mo | AFTER re-dispatch t/mo | Δ t/mo | Change % | December TARGET t | Coverage after
SAP | 2315483 | 2711229 | 395746 | 17.09% | 2311213 | 117.3%
LIM-TOS | 1331853 | 1331853 | 0 | 0% | 1326082 | 100.4%
LIM-LD | 1397954 | 992469 | -405485 | -29.01% | 992213 | 100%
of which SAP stocked at FeNi KM0 (KR 52 DT + TF 52 DT reallocated) |  | 395746 | 395746 | inside the SAP row
TOTAL moved | 5045290 | 5035551 | -9739 | -0.193%

## Insights
Insights
1 · The scenarios are separated by LD, nothing else.
SAP and LIM-TOS clear their sales lines in all four scenarios (100.3–100.5%). The whole difference between plans is how much LIM-LD the leftover fleet can move: 92.2–93.0% of its line. TF>HUAFEI is the binding corridor.
2 · The .2 split scenarios move more total tonnes.
3.0.2 predicts ~488 kt more than 3.0.1 (97.7% vs 96.8% of 17.0 Mt); 3.1.2 ~395 kt more than 3.1.1. Splitting leftover LD trucks to POS 6 relieves the saturated HUAFEI corridor - the split is worth roughly half a million tonnes over the quarter.
3 · December is the only month with slack.
Sep-Nov run 93-97% of their distributed sales share in every scenario; December runs 101.7-104.9%. The fleet grows to 1,190-1,280 DT while the remaining target shrinks - December has spare trucks.
4 · Option 1 (park) reaches 100% but wastes capacity.
Parking 26-59 DT lands the total month at exactly 100.0%. Simple, but those trucks produce nothing and the plants build no buffer.
5 · Option 2 (re-dispatch to stock) is strictly better if KM0 can take stock.
Sized to the real goal — LIM-LD at exactly 100% — the cut is 56-104 DT, and re-dispatching them to KR>FENI KM0 + TF>FENI KM0 builds 213-396 kt of kilnable SAP stock at the plant in December while every sales line still clears (SAP rises to 109-117%). Requires KM0 to accept stock.
6 · Where the cuts come from.
In .1 scenarios the donor is TF>HUAFEI RIM (the biggest untensioned LD row); in .2 scenarios the donor is the TF>POS 6 split flow (untargeted by design). No targeted route drops below its own line in any option.